## README
Dynamic Truck Factor (TF) Calibration Framework
Talabira OCP ¦ FMS Production Reconciliation Model ¦ Built from TOMPL Survey vs FMS GPS-Trip Data
PURPOSE
This workbook operationalises the weighted Dynamic Truck Factor (TF) framework used to correct systematic under-reporting of Overburden (OB) production in the Fleet Management System (FMS). The FMS estimates volume as Trips x TF, using a fixed OEM truck factor that was never revalidated against ground-truth survey data. TOMPL's independent survey showed the April 2026 FMS under-reported OB volume by 16.1% against a CIL-mandated tolerance of +/-2%.
HOW TO USE THIS WORKBOOK
| Tab | Contents
| Assumptions | Global inputs: OEM truck factors, CIL tolerance, weighting rules. Edit yellow cells only.
| Phase 1 - Monthly | Months 1-12. Weighted epsilon calc, first & second TF recalibration, Gate 1 check.
| Phase 2 - Quarterly | Months 13-36 (incl. one-year extension). Quarterly epsilon, annual TF update, Gate 2 check.
| Phase 3 - Annual | Month 37 onwards. Single annual audit survey, pass/fail against CIL tolerance.
| Summary Dashboard | Full 48-month journey: TF evolution, error reduction, and the production-volume recovered by the fix.
COLOUR LEGEND
| Blue text | Hardcoded input / source data
| Black text | Live formula (recalculates automatically)
| Green text | Link to another sheet
| Yellow fill | Key assumption - editable
| Green fill | Gate criterion PASSED
| Red fill | Gate criterion FAILED
CORE FORMULA
Deviation: epsilon = (V_survey - V_FMS) / V_FMS
Weighted average deviation: epsilon_avg = SUM(w * epsilon) / SUM(w)
Recalibrated Truck Factor: TF_new = TF_old * (1 + epsilon_avg)

## Assumptions
Global Assumptions
Edit yellow cells to re-run the entire model
OEM TRUCK FACTORS (cum per trip) - AS-IS, NEVER PREVIOUSLY REVALIDATED
| Truck Class | OEM TF (cum) | Source / Note
| Small | 13 | OEM nameplate factor, in use since FMS commissioning
| Medium | 25 | OEM nameplate factor, in use since FMS commissioning
| Big | 42 | OEM nameplate factor, in use since FMS commissioning
REGULATORY & CONTROL LIMITS
| Parameter | Value | Note
| CIL tolerance (FMS vs Survey) | 2% | Max allowable FMS-vs-survey divergence for this mine class
| Gate 1 pass threshold (per-month epsilon) | 5% | Each of last 3 months of Phase 1 must be below this
| Gate 1 anomaly ceiling (any single month) | 8% | No month in the calibration window may exceed this
| Gate 1 TF-stability threshold (cum) | 1 | TF change between Month 6 and Month 12 update must be below this
| Gate 2 pass threshold (per-quarter epsilon) | 5% | Each quarter must be below this
| Gate 2 weighted-average ceiling | 3% | Annual weighted epsilon_avg must be below this
| Gate 2 anomaly ceiling (any single quarter) | 8% | No quarter may exceed this
| Gate 2 TF-stability threshold (cum) | 0.5 | TF change between successive annual updates must be below this
| Phase 3 audit threshold (annual epsilon) | 2% | Annual audit epsilon must stay below this or TF is re-opened for correction
| Reference trips per month (medium class) | 48000 | Used only for the illustrative overcorrection-avoided example
WEIGHT ASSIGNMENT PROTOCOL
| Month condition | Weight | Rationale
| Clean month (no known data-quality issue) | 1 | Full confidence in epsilon reading
| Minor issue (e.g. short GPS outage) | 0.7 | Partially reliable
| Major hardware/process fault (e.g. dumpswitch failure) | 0.3 | Low confidence; epsilon likely inflated by noise, not structural TF error

## Phase 1 - Monthly
Phase 1 - Monthly Survey Calibration (Months 1-12)
Weighted deviation is calculated twice: Month 6 (first TF update) and Month 12 (second TF update + Gate 1 check)
MONTHS 1-6 : APR 2026 - SEP 2026 (pre-calibration, OEM TF still in force)
| Month | V_survey (cum) | V_FMS (cum) | Epsilon % | Data-quality issue | Weight | w x Epsilon
| Apr-26 | 1605346 | 1336625 | 20.1% | Dumpswitch broken | 0.3 | 6.031%
| May-26 | 1616656 | 1528807 | 5.746% | Clean | 1 | 5.746%
| Jun-26 | 1590000 | 1502000 | 5.859% | Clean | 1 | 5.859%
| Jul-26 | 1640000 | 1548000 | 5.943% | Clean | 1 | 5.943%
| Aug-26 | 1575000 | 1470000 | 7.143% | GPS outage 3 days | 0.7 | 5%
| Sep-26 | 1620000 | 1538000 | 5.332% | Clean | 1 | 5.332%
TF UPDATE 1 - MONTH 6 (October 2026): weighted average of Apr-Sep window
| Weighted epsilon_avg = |  |  |  | 6.782%
| Truck class | Old TF (cum) | New TF = Old x (1+eps_avg)
| Small | 13 | 13.8817
| Medium | 25 | 26.6956
| Big | 42 | 44.8485
MONTHS 7-12 : OCT 2026 - MAR 2027 (post Update-1, residual epsilon under new TF)
New TF applied from October 2026. FMS volumes now run on the recalibrated factor; the residual deviation below is what the framework is designed to leave behind - small and centred near zero.
| Month | Residual Epsilon % (post-update) |  | Data-quality issue | Weight | w x Epsilon
| Oct-26 | 1.2% |  | Clean | 1 | 1.2%
| Nov-26 | 0.9% |  | Clean | 1 | 0.9%
| Dec-26 | 1.5% |  | Clean | 1 | 1.5%
| Jan-27 | 0.8% |  | Clean | 1 | 0.8%
| Feb-27 | 1.1% |  | Clean | 1 | 1.1%
| Mar-27 | 1% |  | Clean | 1 | 1%
TF UPDATE 2 - MONTH 12 (March 2027): weighted average of Oct-Mar residuals
| Weighted epsilon_avg (Oct-Mar) |  |  |  | 1.083%
| Truck class | TF after Update 1 | TF after Update 2 | Change (cum)
| Small | 13.8817 | 14.0321 | 0.15038
| Medium | 26.6956 | 26.9848 | 0.2892
| Big | 44.8485 | 45.3344 | 0.48586
GATE 1 CHECK - proceed to Phase 2 only if ALL criteria pass
| Criterion | Actual | Threshold | Result
| Last 3 months (Jan-Mar) each below threshold | 1.1% | 5% | PASS
| No month in the current (Oct-Mar) window exceeds anomaly ceiling | 1.5% | 8% | PASS
| TF change, Month 6 to Month 12 (Medium class) | 0.2892 | 1 | PASS
| GATE 1 OVERALL RESULT |  |  | PASS - PROCEED TO PHASE 2
Note on F6: Dumpswitch (payload sensor) malfunction inflated apparent deviation - downweighted per protocol.
Note on F10: 3-day GPS blackout reduced trip logging reliability - partial downweight.
Note on C23: Illustrative residual values: post-calibration epsilon is assumed to converge close to zero, consistent with structural error having been corrected in Update 1.
Note on C41: TF change is rounded to 1 decimal place (0.1 cum) before comparison to the threshold, matching the mine's TF reporting precision.

## Phase 2 - Quarterly
Phase 2 - Quarterly Survey Calibration (Months 13-36)
Survey frequency drops from monthly to quarterly once Gate 1 is passed. TF is now updated once a year.
YEAR 2 : Q1-Q4 (Apr 2027 - Mar 2028), TF held at Month-12 value throughout
| Quarter | V_survey (cum) | V_FMS (cum) | Epsilon % | Data-quality issue | Weight | w x Epsilon
| Q1 Apr-Jun 27 | 4820000 | 4604000 | 4.692% | Clean | 1 | 4.692%
| Q2 Jul-Sep 27 | 4910000 | 4725000 | 3.915% | Clean | 1 | 3.915%
| Q3 Oct-Dec 27 | 4750000 | 4510000 | 5.322% | One month GPS outage | 0.7 | 3.725%
| Q4 Jan-Mar 28 | 5020000 | 4825000 | 4.041% | Clean | 1 | 4.041%
ANNUAL TF UPDATE - MONTH 24 (March 2028)
| Weighted epsilon_avg (Q1-Q4) |  |  |  | 4.425%
| Truck class | TF after Month 12 | TF after Month 24 | Change (cum)
| Small | 14.0321 | 14.653 | 0.62095
| Medium | 26.9848 | 28.1789 | 1.1941
| Big | 45.3344 | 47.3406 | 2.0062
GATE 2 CHECK - MONTH 24
| Criterion | Actual | Threshold | Result
| All 4 quarters below per-quarter threshold | 5.322% | 5% | FAIL
| Weighted epsilon_avg below ceiling | 4.425% | 3% | FAIL
| No quarter exceeds anomaly ceiling | 5.322% | 8% | PASS
| TF change, Month 12 to Month 24 (Medium class) | 1.1941 | 0.5 | FAIL
| GATE 2 RESULT (Month 24) |  |  | FAIL - EXTEND PHASE 2 BY 1 YEAR
EXTENDED PHASE 2 : Q5-Q8 (Apr 2028 - Mar 2029), TF held at Month-24 value
Because Gate 2 failed at Month 24, the quarterly survey continues for one further year instead of stepping down to an annual audit.
| Quarter | Epsilon % |  | Data-quality issue | Weight | w x Epsilon
| Q5 Apr-Jun 28 | 1.8% |  | Clean | 1 | 1.8%
| Q6 Jul-Sep 28 | 2.1% |  | Clean | 1 | 2.1%
| Q7 Oct-Dec 28 | 1.5% |  | Clean | 1 | 1.5%
| Q8 Jan-Mar 29 | 1.9% |  | Clean | 1 | 1.9%
ANNUAL TF UPDATE - MONTH 36 (March 2029)
| Weighted epsilon_avg (Q5-Q8) |  |  |  | 1.825%
| Truck class | TF after Month 24 | TF after Month 36 | Change (cum)
| Small | 14.653 | 14.9204 | 0.26742
| Medium | 28.1789 | 28.6932 | 0.51426
| Big | 47.3406 | 48.2045 | 0.86397
GATE 2 RECHECK - MONTH 36
| Criterion | Actual | Threshold | Result
| All 4 quarters below per-quarter threshold | 2.1% | 5% | PASS
| Weighted epsilon_avg below ceiling | 1.825% | 3% | PASS
| No quarter exceeds anomaly ceiling | 2.1% | 8% | PASS
| TF change, Month 24 to Month 36 (Medium class) | 0.51426 | 0.5 | PASS
| GATE 2 RESULT (Month 36) |  |  | PASS - PROCEED TO PHASE 3
Note on C46: TF change is rounded to 1 decimal place (0.1 cum) before comparison to the threshold, matching the mine's TF reporting precision.

## Phase 3 - Annual
Phase 3 - Annual Audit (Month 37 onwards)
FMS becomes the primary production-of-record system; a single survey per year checks it has not drifted.
TF IN FORCE FROM MONTH 37
| Truck class | TF (cum)
| Small | 14.9204
| Medium | 28.6932
| Big | 48.2045
ANNUAL AUDIT - MONTH 48 (March 2030)
| Metric | Value
| Annual survey volume (cum) | 19500000
| Annual FMS volume (cum) | 19167000
| Annual epsilon | 1.737%
AUDIT RESULT
| Criterion | Actual | Threshold | Result
| Annual epsilon within Phase 3 audit threshold | 1.737% | 2% | PASS - NO TF CHANGE NEEDED
FMS is now running within CIL tolerance on an annual-audit cadence, without additional hardware or monthly survey cost.

## Summary Dashboard
48-Month Journey Summary
From 16.1% April-2026 divergence to sub-2% annual-audit compliance, at zero incremental hardware cost
COMPLETE JOURNEY (Medium truck class)
| Time | TF Medium (cum) | Epsilon | Survey cadence | Status
| Start (Apr-26) | 25 | 20.1% | Monthly | CIL FAIL
| Month 6 | 26.6956 | 6.782% | Monthly | Improving
| Month 12 | 26.9848 | 1.083% | Monthly | CIL PASS
| Month 24 | 28.1789 | 4.425% | Quarterly | Fine-tuning
| Month 36 | 28.6932 | 1.825% | Quarterly | Stable
| Month 48 | 28.6932 | 1.737% | Annual | FMS PRIMARY
VALUE OF THE FIX
| Metric | Value | Note
| OEM TF, start (cum) | 25
| Calibrated TF, Month 48 (cum) | 28.6932
| Total correction per trip (cum) | 3.6932
| Total correction (% of OEM TF) | 14.77%
| Reference trips per month | 48000
| Previously-unrecorded volume (cum/month) | 177272.1168 | OB volume that was always being excavated but never recorded in FMS before calibration
SURVEY COST TRAJECTORY
| Phase | Survey cadence | Relative annual survey cost
| Phase 1 (Months 1-12) | Monthly (12 surveys/yr) | 100%
| Phase 2 (Months 13-36) | Quarterly (4 surveys/yr) | 33%
| Phase 3 (Month 37+) | Annual (1 survey/yr) | 8%
| Survey cost reduction, Phase 1 to Phase 3 | 92%
ERROR-REDUCTION CHART
(Chart plots Epsilon % at each milestone above; CIL 2% limit shown as reference)
CIL Limit
2%
2%
2%
2%
2%
2%